## Sheet1
week | Tast
2023-01-01 | Create GitHub Repo
15/1/2023 | Add python files
2023-01-02 | Add MakeFile and requirments.txt Files
15/2/2023 | Plan Github Action
2023-01-03 | Build GitHub Actions
15/3/2023 | Test GitHub Actions
Goals
GitHub Repo Created
File added successfully
Passed GitHub Actions test
week | Tast
2023-01-04 | Create Azure account
15/4/2023 | Create and activated python environment
2023-01-05 | Connect with Github repo and pull the project
15/5/2023 | make_prediction.sh
2023-01-06 | Creating Azure app service
15/6/2023 | make_prediction_azure.sh
Goals
Azure account is available
wep app service is created
prediction passed
week | Task
2023-01-07 | Create Azure DevOps organization
15/7/2023 | Create linux VM
2023-01-08 | Create agent contains docker for build and deploy
15/8/2023 | Create Azure pipeline
2023-01-09 | Implement testing pipeline
15/9/2023 | Implement testing pipeline
Goals
pipeline and Web App build
week | Task
2023-01-10 | Documentation
15/10/2023 | cleaning code
2023-01-11 | modify readme file
2023-01-12 | lunch the app
Goals
App was lunched